## WEEK
TSPi Weekly Status Report - Form WEEK
Name | Alvaro Suarez | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-05-10 | Cycle No. | 2 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 8.3333 | 24.1667
Project hours this cycle to date |  |  | 25 | 24.1667
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 25 | 24.1667 | 25 | 8.3333 | 1
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 25 | 24.1667 | 25
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 3.25 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 3.9167 | 0 | 1 | 0
Diseño T2 |  |  | 1.688 | 4 | 0 | 1 | 0
Documentacion T2 |  |  | 1.5192 | 3.4167 | 1.5192 | 1 | 1
Code T2 |  |  | 7.596 | 4.4167 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 2.6667 | 1.688 | 1 | 1
PostMortem T2 |  |  | 0.844 | 2.5 | 0.844 | 1 | 1
Totals |  |  | 16.88 | 24.1667 | 13.3352
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## TASK Planning
TSPi Task Planning Template - Form TASK
Name | Alvar Suarez |  |  | Date | 2015-05-10
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle | 2
2015-04-04
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 2 | Planning T2 | 5 | 1.688 | 8.44 | 5 | PAGINAS | 0.2 | 1 | 10 | 10 | 3.25 | 3.25 | 1
REQ | 2 | Requerimientos T2 | 5 | 1.8568 | 9.284 | 14.284 | PAGINAS | 0.2 | 1 | 11 | 21 | 3.9167 | 7.1667 | 1
DES | 2 | Diseño T2 | 5 | 1.688 | 8.44 | 22.724 | PAGINAS | 0.2 | 1 | 10 | 31 | 4 | 11.1667 | 2
DOC | 2 | Documentacion T2 | 5 | 1.5192 | 7.596 | 30.32 | PAGINAS | 0.2 | 1 | 9 | 40 | 3.4167 | 14.5833 | 2
CODE | 2 | Code T2 | 5 | 7.596 | 37.98 | 68.3 | LOC | 11 | 2,3 | 45 | 85 | 4.4167 | 19 | 2,3
T | 2 | Test T2 | 5 | 1.688 | 8.44 | 76.74 | LOC | 3 | 3 | 10 | 95 | 2.6667 | 21.6667 | 3
PM | 2 | PostMortem T2 | 5 | 0.844 | 4.22 | 80.96 | PAGINAS | 0.2 | 3 | 5 | 100 | 2.5 | 24.1667 | 3
|  |  |  | 16.88 | 84.4 |  |  |  |  | 100 | 100 | 24.1667

## LOGT
TSPi Time Recording Log – Form LOGT
Name |  | Alvaro Suarez |  |  |  |  | Date |  | 2015-05-10
Team |  | Umbrella |  |  |  |  | Instructor |  | Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 2
Date | Start | Stop | Interruption | Delta | Phase/ | Comp-onent |  | Comments
|  |  | Time | Time | Task
2015-04-25 | 8:00 | 10:00 | 0 | 120 | Plan |  |  |  |  | 2:00 | 120 |  | min | hour
2015-04-25 | 10:30 | 12:00 | 15 | 75 | Plan |  |  |  |  | 1:30 | 90 | PLAN | 195 | 3.25
2015-05-02 | 8:00 | 9:00 | 20 | 40 | Design |  |  |  |  | 1:00 | 60 | REQ | 235 | 3.9167
2015-05-02 | 10:00 | 14:00 | 40 | 200 | Design |  |  |  |  | 4:00 | 240 | DES | 240 | 4
2015-05-02 | 15:00 | 20:00 | 65 | 235 | Req |  |  |  |  | 5:00 | 300 | DOC | 205 | 3.4167
2015-05-02 | 8:00 | 12:00 | 35 | 205 | Doc |  |  |  |  | 4:00 | 240 | CODE | 265 | 4.4167
2015-05-09 | 11:00 | 13:00 | 20 | 100 | Code |  |  |  |  | 2:00 | 120 | T | 160 | 2.6667
2015-05-09 | 15:00 | 18:00 | 15 | 165 | Code |  |  |  |  | 3:00 | 180 | PM | 150 | 2.5
2015-05-09 | 19:00 | 22:00 | 20 | 160 | Test |  |  |  |  | 3:00 | 180
2015-05-10 | 16:00 | 19:00 | 30 | 150 | Post |  |  |  |  | 3:00 | 180
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## SCHEDULE
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Alvaro Suarez |  |  |  |  | Date |  |  | 2015-05-10
Team |  | Umbrella |  |  |  |  | Instructor |  |  | Daniel Benavides
Part/Level | [6 empty] | Cycle |  |  | 2
|  |  | Plan |  |  | Actual
Week No. | Date |  | Direct Hours | Cumulative Hours | Cumulative Plan Value | Hours |  | Cumulative Hours | Week Earn Value |  | Cumulative Earn Value
1 | 2015-04-25 |  | 8.3333 | 8.3333 | 33.3333 | 7.1667 |  | 7.1667 | 1.688 |  | 1.688
2 | 2015-05-02 |  | 8.3333 | 16.6667 | 66.6667 | 9.625 |  | 16.7917 | 5.3172 |  | 7.0052
3 | 2015-05-09 |  | 8.3333 | 25 | 100 | 7.375 |  | 24.1667 | 6.33 |  | 13.3352
25

## SUMTASK
TSPi Task Summary - Form SUMTASK
Name | Alvaro Suarez
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 3.25 | 1.9254
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 4 | 2.3697
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 4.4167 | 0.58145
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 2.6667 | 1.5798
Postmortem | 0.844 | 2.5 | 2.9621
Total time (minutes) | 810.24 | 1010 | 1.2465
Total time (hours) | 13.504 | 16.8333