## SUMTASK
TSPi Task Summary - Form SUMTASK
Name | Umbrella
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 44 | 1.1488 | 38.3 | 368 | 28.5 | 12.9123
Total |  |  |  | 38.3
Time in Phase | Plan | Actual | % | Base Times
Planning | 8.44 | 18 | 2.1327
Research | 0 | 0 | 0
Outline/High-level design | 8.44 | 21 | 2.4882
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 37.98 | 28.5 | 0.75039
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 8.44 | 6.3333 | 0.75039
Postmortem | 4.22 | 18.1667 | 4.3049
Total time (minutes) | 4051.2 | 5520 | 1.3626
Total time (hours) | 67.52 | 92

## DEV
TSPi Task Summary - Form SUMTASK
Name | Javier Virviescas
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 3.1667 | 1.876
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 4.6667 | 2.7646
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 9.5833 | 1.2616
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 1.5 | 0.88863
Postmortem | 0.844 | 4.1667 | 4.9368
Total time (minutes) | 810.24 | 1385 | 1.7094
Total time (hours) | 13.504 | 23.0833

## PLAN
TSPi Task Summary - Form SUMTASK
Name | Gabriel Castillo
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 4.5833 | 2.7152
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 4.1667 | 2.4684
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 4.8333 | 0.6363
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 0 | 0
Postmortem | 0.844 | 2 | 2.3697
Total time (minutes) | 810.24 | 935 | 1.154
Total time (hours) | 13.504 | 15.5833

## QUA
TSPi Task Summary - Form SUMTASK
Name | Erica Prado
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 3.3333 | 1.9747
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 3.75 | 2.2216
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 4.8333 | 0.6363
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 0 | 0
Postmortem | 0.844 | 5.3333 | 6.3191
Total time (minutes) | 810.24 | 1035 | 1.2774
Total time (hours) | 13.504 | 17.25

## SUPP
TSPi Task Summary - Form SUMTASK
Name | Oscar Morneo
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 3.6667 | 2.1722
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 4.4167 | 2.6165
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 4.8333 | 0.6363
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 2.1667 | 1.2836
Postmortem | 0.844 | 4.1667 | 4.9368
Total time (minutes) | 810.24 | 1155 | 1.4255
Total time (hours) | 13.504 | 19.25

## LEAD
TSPi Task Summary - Form SUMTASK
Name | Alvaro Suarez
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T2 | LOC | 11 | 86.8878 | 7.596
Total |  |  |  | 7.596
Time in Phase | Plan | Actual | % | Base Times
Planning | 1.688 | 3.25 | 1.9254
Research | 0 | 0 | 0
Outline/High-level design | 1.688 | 4 | 2.3697
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.596 | 4.4167 | 0.58145
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.688 | 2.6667 | 1.5798
Postmortem | 0.844 | 2.5 | 2.9621
Total time (minutes) | 810.24 | 1010 | 1.2465
Total time (hours) | 13.504 | 16.8333