## Week
TSPi Weekly Status Report - Form WEEK
Name | Umbrella | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 25 | 0
Project hours this cycle to date |  |  | 75 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 5 | 24.1667 | 0 | 0
Development Manager |  |  | 5 | 24.0833
Planning Manager |  |  | 5 | 24.75
Quality/Process Manager |  |  | 5 | 24.3333
Support Manager |  |  | 5 | 24.3333
Totals |  |  | 25 | 121.6667 | 0
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 5 | 17.6667 | 5 | 1 | 1
Requerimientos T1 |  |  | 5 | 25.75 | 5 | 1 | 1
Diseño T1 |  |  | 6 | 20.3333 | 6 | 1 | 1
Documentacion T1 |  |  | 3 | 9.75 | 3 | 1 | 1
Code T1 |  |  | 38.3 | 20.8333 | 38.3 | 1 | 1
Test T1 |  |  | 6 | 4.1667 | 6 | 1 | 1
PostMortem T1 |  |  | 4 | 8.6667 | 4 | 1 | 1
Totals |  |  | 67.3 | 107.1667 | 67.3
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items
Note on F27: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego

## Leader
TSPi Weekly Status Report - Form WEEK
Name | Alvaro Suarez | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42134 | Cycle No. | 2 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 8.3333 | 24.1667
Project hours this cycle to date |  |  | 25 | 24.1667
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 25 | 24.1667 | 25 | 8.3333 | 1
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 25 | 24.1667 | 25
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 3.25 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 3.9167 | 0 | 1 | 0
Diseño T2 |  |  | 1.688 | 4 | 0 | 1 | 0
Documentacion T2 |  |  | 1.5192 | 3.4167 | 1.5192 | 1 | 1
Code T2 |  |  | 7.596 | 4.4167 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 2.6667 | 1.688 | 1 | 1
PostMortem T2 |  |  | 0.844 | 2.5 | 0.844 | 1 | 1
Totals |  |  | 16.88 | 24.1667 | 13.3352
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Support
TSPi Weekly Status Report - Form WEEK
Name | Erica Prado | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 2 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 8.3333 | 24.3333
Project hours this cycle to date |  |  | 25 | 24.3333
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Quality Manager |  |  | 15 | 24.3333 | 15 | 8.3333 | 1
Development Manager
Planning Manager
Team Leader
Support Manager
Totals |  |  | 15 | 24.3333 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 3.3333 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 7.0833 | 1.8568 | 1 | 1
Diseño T2 |  |  | 1.688 | 3.75 | 1.688 | 1 | 1
Documentacion T2 |  |  | 1.5192 | 0 | 0 | 1 | 0
Code T2 |  |  | 7.596 | 1 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 0 | 0 | 1 | 0
PostMortem T2 |  |  | 0.844 | 0 | 0 | 1 | 0
Totals |  |  | 16.88 | 15.1667 | 12.8288
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Quality
TSPi Weekly Status Report - Form WEEK
Name | Erica Prado | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42134 | Cycle No. | 2 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 8.3333 | 24.3333
Project hours this cycle to date |  |  | 25 | 24.3333
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Quality Manager |  |  | 15 | 24.3333 | 15 | 8.3333 | 1
Development Manager
Planning Manager
Team Leader
Support Manager
Totals |  |  | 15 | 24.3333 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 3.3333 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 7.0833 | 1.8568 | 1 | 1
Diseño T2 |  |  | 1.688 | 3.75 | 1.688 | 1 | 1
Documentacion T2 |  |  | 1.5192 | 0 | 0 | 1 | 0
Code T2 |  |  | 7.596 | 1 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 0 | 0 | 1 | 0
PostMortem T2 |  |  | 0.844 | 0 | 0 | 1 | 0
Totals |  |  | 16.88 | 15.1667 | 12.8288
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Planning
TSPi Weekly Status Report - Form WEEK
Name | Gabriel Castillo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 24.75
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned | Percentage
Team Member Weekly Data |  |  | Planned | Actual | Value | Value | Completed
Planning Manager |  |  | 15 | 24.75 | 15 | 5 | 1
Development Manager
Team Leader
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 24.75 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 4.5833 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 3.8333 | 1.8568 | 1 | 1
Diseño T2 |  |  | 1.688 | 4.1667 | 1.688 | 1 | 1
Documentacion T2 |  |  | 1.5192 | 5.3333 | 1.5192 | 1 | 1
Code T2 |  |  | 7.596 | 4.8333 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 0 | 0 | 1 | 0
PostMortem T2 |  |  | 0.844 | 2 | 0.844 | 1 | 1
Totals |  |  | 16.88 | 24.75 | 15.192
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Development
TSPi Weekly Status Report - Form WEEK
Name | Javier Virviescas | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 24.0833
Project hours this cycle to date |  |  | 25 | 24.0833
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 25 | 24.0833 | 25 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 25 | 24.0833 | 25
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T2 |  |  | 1.688 | 3.1667 | 1.688 | 1 | 1
Requerimientos T2 |  |  | 1.8568 | 0 | 0 | 1 | 0
Diseño T2 |  |  | 1.688 | 4.6667 | 1.688 | 1 | 1
Documentacion T2 |  |  | 1.5192 | 1 | 0 | 1 | 0
Code T2 |  |  | 7.596 | 9.5833 | 7.596 | 1 | 1
Test T2 |  |  | 1.688 | 1.5 | 1.688 | 1 | 1
PostMortem T2 |  |  | 0.844 | 4.1667 | 0.844 | 1 | 1
Totals |  |  | 16.88 | 24.0833 | 13.504
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items