## SUMP
TSPi Plan Summary - Form SUMP
Name | Umbrella |  | Date | 2015-04-15
Team |  |  | Instructor | Daniel Benavides
Part/Level |  |  | Cycle | 1
Product Size | Plan | Actual
Requirements pages (SRS) | 1 | 9
Other text pages | 0
High-level design pages (SDS) | 1 | 1
Detailed design lines
Base LOC (B) (measured)
Deleted LOC (D) | 50 | 40
| (Estimated) | (Counted)
Modified LOC (M) | 50 | 20
| (Estimated) | (Counted)
Added LOC (A) | 100 | 308
| (N-M) | (T-B+D-R)
Reused LOC (R) | 0 | 0
| (Estimated) | (Counted)
Total New & Changed LOC (N)
| (Estimated) | (A+M)
Total LOC (T) | 200 | 368
| (N+B-M-D+R) | (Measured)
Total New Reuse LOC
Estimated Object LOC (E)
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual |  | Actual %
Management and miscellaneous | 0 | 0 |  | 0%
Launch and strategy | 0 | 0 |  | 0%
Planning | 5 | 7.6 |  | 65.79%
Requirements | 5 | 8.12 |  | 61.58%
System test plan | 0 | 0 |  | 0%
Requirements inspection | 0 | 0 |  | 0%
High-level design | 2 | 1.7259 |  | 115.9%
Integration test plan | 0 | 0 |  | 0%
High-level design inspection | 0 | 0 |  | 0%
Implementation planning | 0 | 0 |  | 0%
Detailed design | 4 | 3.4518 |  | 115.9%
Detailed design review | 0 | 0 |  | 0%
Test development | 6 | 0 |  | 0%
Detailed design inspection | 0 | 0 |  | 0%
Code | 38.3 | 5.58 |  | 686.4%
Code review | 0 | 0 |  | 0%
Compile | 0 | 0 |  | 0%
Code inspection | 0 | 0 |  | 0%
Unit test | 0 | 0 |  | 0%
Build and integration | 0 | 0 |  | 0%
System test | 0 | 0 |  | 0%
Documentation | 3 | 1.47 |  | 204.1%
Postmortem | 4 | 0.75 |  | 533.3%
Total | 67.3 | 28.6977 |  | 234.5%
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual |  | Actual %
Strategy and Planning | 0 | 0 |  | 0%
Requirements | 0 | 0 |  | 0%
System test plan | 0 | 0 |  | 0%
Requirements inspection | 0 | 0 |  | 0%
High-level design | 0 | 0 |  | 0%
Integration test plan | 0 | 0 |  | 0%
High-level design inspection | 0 | 0 |  | 0%
Detailed design | 0 | 0 |  | 0%
Detailed design review | 0 | 0 |  | 0%
Test development | 0 | 0 |  | 0%
Detailed design inspection | 0 | 0 |  | 0%
Code | 2 | 20 |  | 1000%
Code review | 0 | 0 |  | 0%
Compile | 0 | 0 |  | 0%
Code inspection | 0 | 0 |  | 0%
Unit Test | 1 | 0 |  | 0%
Build and integration | 0 | 0 |  | 0%
System test | 0 | 0 |  | 0%
Total Development | 3 | 20 |  | 0
Defects Removed | Plan | Actual |  | Actual %
Strategy and Planning | 0 | 0 |  | 0%
Requirements | 0 | 0 |  | 0%
System test plan | 0 | 0 |  | 0%
Requirements inspection | 0 | 0 |  | 0%
High-level design | 0 | 0 |  | 0%
Integration test plan | 0 | 0 |  | 0%
High-level design inspection | 0 | 0 |  | 0%
Detailed design | 0 | 0 |  | 0%
Detailed design review | 0 | 0 |  | 0%
Test development | 0 | 0 |  | 0%
Detailed design inspection | 0 | 0 |  | 0%
Code | 2 | 20 |  | 1000%
Code review | 0 | 0 |  | 0%
Compile | 0 | 0 |  | 0%
Code inspection | 0 | 0 |  | 0%
Unit Test | 1 | 0 |  | 0%
Build and integration | 0 | 0 |  | 0%
System test | 0 | 0 |  | 0%
Total Development | 3 | 20

## DEV
TSPi Task Planning Template - Form TASK
Name | Javier Virviescas |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Development Manager | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 0.83333 | 0.83333 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 0 | 0.83333 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 1.4167 | 2.25 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 0 | 2.25 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 2.5833 | 4.8333 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0.33333 | 5.1667 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 0.3 | 5.4667 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 5.4667

## PLAN
TSPi Task Planning Template - Form TASK
Name | Gabriel Castillo |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Planning Manager | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 2.5 | 2.5 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 2.7 | 5.2 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 0.66667 | 5.8667 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 0 | 5.8667 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 0 | 5.8667 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0 | 5.8667 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 0.45 | 6.3167 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 6.3167

## QUA
TSPi Task Planning Template - Form TASK
Name | Erica Prado |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 2.8667 | 2.8667 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 2.7167 | 5.5833 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 2.25 | 7.8333 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 0.46667 | 8.3 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 0 | 8.3 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0 | 8.3 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 0 | 8.3 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 8.3

## SUPP
TSPi Task Planning Template - Form TASK
Name | Oscar Moreno |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 0.7 | 0.7 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 0 | 0.7 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 0.9 | 1.6 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 0 | 1.6 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 1 | 2.6 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0.5 | 3.1 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 1 | 4.1 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 4.1

## LEAD
TSPi Task Planning Template - Form TASK
Name | Alvar Suarez |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
42098
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 0.7 | 0.7 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 0 | 0.7 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 0 | 0.7 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 1 | 1.7 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 1 | 2.7 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0.5 | 3.2 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 0.17 | 3.37 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 3.37