## SUMTASK
TSPi Task Summary - Form SUMTASK
Name | Umbrella
Team | Umbrella
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T1 | LOC | 44 | 1.1488 | 38.3 | 368 | 3.5833 | 102.6977
Total |  |  |  | 38.3
Time in Phase | Plan | Actual | % | Base Times
Planning | 5 | 9.7667 | 1.9533
Research | 0 | 0 | 0
Outline/High-level design | 6 | 6.5833 | 1.0972
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 38.3 | 3.5833 | 0.09356
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 6 | 0.83333 | 0.13889
Postmortem | 4 | 0.92 | 0.23
Total time (minutes) | 3558 | 1301.2 | 0.36571
Total time (hours) | 59.3 | 21.6867

## DEV
TSPi Task Summary - Form SUMTASK
Name
Team
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Code T1 | LOC | 11 | 17.2324 | 7.66
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Total |  |  |  | 7.66
Time in Phase | Plan | Actual | % | Base Times
Planning | 1 | 0.83333 | 0.83333
Research | 0 | 0 | 0
Outline/High-level design | 1.2 | 1.4167 | 1.1806
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.66 | 2.5833 | 0.33725
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.2 | 0.33333 | 0.27778
Postmortem | 0.8 | 0.3 | 0.375
Total time (minutes) | 711.6 | 328 | 0.46093
Total time (hours) | 11.86 | 5.4667

## PLAN
TSPi Task Summary - Form SUMTASK
Name
Team
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Code T1 | LOC | 11 | 17.2324 | 7.66
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Total |  |  |  | 7.66
Time in Phase | Plan | Actual | % | Base Times
Planning | 1 | 2.5 | 2.5
Research | 0 | 0 | 0
Outline/High-level design | 1.2 | 0.66667 | 0.55556
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.66 | 0 | 0
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.2 | 0 | 0
Postmortem | 0.8 | 0.45 | 0.5625
Total time (minutes) | 711.6 | 217 | 0.30495
Total time (hours) | 11.86 | 3.6167

## QUA
TSPi Task Summary - Form SUMTASK
Name
Team
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T1 | LOC | 11 | 86.1619 | 7.66
Total |  |  |  | 7.66
Time in Phase | Plan | Actual | % | Base Times
Planning | 1 | 2.8667 | 2.8667
Research | 0 | 0 | 0
Outline/High-level design | 1.2 | 2.25 | 1.875
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.66 | 0 | 0
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.2 | 0 | 0
Postmortem | 0.8 | 0 | 0
Total time (minutes) | 711.6 | 307 | 0.43142
Total time (hours) | 11.86 | 5.1167

## SUPP
TSPi Task Summary - Form SUMTASK
Name
Team
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T1 | LOC | 11 | 17.2324 | 7.66
Total |  |  |  | 7.66
Time in Phase | Plan | Actual | % | Base Times
Planning | 1 | 2.8667 | 2.8667
Research | 0 | 0 | 0
Outline/High-level design | 1.2 | 2.25 | 1.875
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.66 | 0 | 0
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.2 | 0 | 0
Postmortem | 0.8 | 0 | 0
Total time (minutes) | 711.6 | 307 | 0.43142
Total time (hours) | 11.86 | 5.1167

## LEAD
TSPi Task Summary - Form SUMTASK
Name
Team
Part/Level
Products of the task
Task users/customers
Overall requirements/message
Specifications/constraints
Product elements | Size | Plan | Plan | Plan | Act. | Act. | Act.
| Unit | Units | Rate | Time | Units | Time | Rate
Code T1 | LOC | 11 | 17.2324 | 7.66
Total |  |  |  | 7.66
Time in Phase | Plan | Actual | % | Base Times
Planning | 1 | 0.7 | 0.7
Research | 0 | 0 | 0
Outline/High-level design | 1.2 | 0 | 0
Peer review and correct | 0 | 0 | 0
Draft/Detailed-level design | 0 | 0 | 0
Design review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Implementation/Rewrite | 7.66 | 1 | 0.13055
Review | 0 | 0 | 0
Peer review and correct | 0 | 0 | 0
Test/Trial use | 1.2 | 0.5 | 0.41667
Postmortem | 0.8 | 0.17 | 0.2125
Total time (minutes) | 711.6 | 142.2 | 0.19983
Total time (hours) | 11.86 | 2.37