## Week
TSPi Weekly Status Report - Form WEEK
Name | Umbrella | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 25 | 0
Project hours this cycle to date |  |  | 75 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 5 | 25.6667 | 0 | 0
Development Manager |  |  | 5 | 23.1667
Planning Manager |  |  | 5 | 26.5667
Quality/Process Manager |  |  | 5 | 24.35
Support Manager |  |  | 5 | 22.7833
Totals |  |  | 25 | 122.5333 | 0
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 5 | 18.7 | 5 | 1 | 1
Requerimientos T1 |  |  | 5 | 31.55 | 5 | 1 | 1
Diseño T1 |  |  | 6 | 19.0333 | 6 | 1 | 1
Documentacion T1 |  |  | 3 | 11.3667 | 3 | 1 | 1
Code T1 |  |  | 38.3 | 23.3833 | 38.3 | 1 | 1
Test T1 |  |  | 6 | 5 | 6 | 1 | 1
PostMortem T1 |  |  | 4 | 11.6167 | 4 | 1 | 1
Totals |  |  | 67.3 | 120.65 | 67.3
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items
Note on F27: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego

## Leader
TSPi Weekly Status Report - Form WEEK
Name | Alvaro Suarez | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 25.6667
Project hours this cycle to date |  |  | 15 | 25.6667
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 25.6667 | 15 | 5 | 1
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 25.6667 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 3.3333 | 1 | 1 | 1
Requerimientos T1 |  |  | 1 | 4 | 0 | 1 | 0
Diseño T1 |  |  | 1.2 | 4.3333 | 0 | 1 | 0
Documentacion T1 |  |  | 0.6 | 4.3333 | 0.6 | 1 | 1
Code T1 |  |  | 7.66 | 4.5 | 7.66 | 1 | 1
Test T1 |  |  | 1.2 | 1.5 | 1.2 | 1 | 1
PostMortem T1 |  |  | 0.8 | 3.6667 | 0.8 | 1 | 1
Totals |  |  | 13.46 | 25.6667 | 11.26
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Support
TSPi Weekly Status Report - Form WEEK
Name | Oscar Morneo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 22.7833
Project hours this cycle to date |  |  | 15 | 22.7833
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Support Manager |  |  | 15 | 22.7833 | 15 | 5 | 1
Development Manager
Planning Manager
Quality/Process Manager
Team Leader
Totals |  |  | 15 | 22.7833 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 3.5833 | 1 | 1 | 1
Requerimientos T1 |  |  | 1 | 6.0667 | 1 | 1 | 1
Diseño T1 |  |  | 1.2 | 3.3833 | 1.2 | 1 | 1
Documentacion T1 |  |  | 0.6 | 0 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 5 | 7.66 | 1 | 1
Test T1 |  |  | 1.2 | 2 | 1.2 | 1 | 1
PostMortem T1 |  |  | 0.8 | 2.75 | 0.8 | 1 | 1
Totals |  |  | 13.46 | 22.7833 | 12.86
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Quality
TSPi Weekly Status Report - Form WEEK
Name | Erica Prado | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 24.35
Project hours this cycle to date |  |  | 15 | 22.82
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Quality Manager |  |  | 15 | 24.35 | 15 | 5 | 1
Development Manager
Planning Manager
Team Leader
Support Manager
Totals |  |  | 15 | 24.35 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 3.1167 | 1 | 1 | 1
Requerimientos T1 |  |  | 1 | 8.0833 | 1 | 1 | 1
Diseño T1 |  |  | 1.2 | 3.5667 | 1.2 | 1 | 1
Documentacion T1 |  |  | 0.6 | 0 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 1 | 7.66 | 1 | 1
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 15.7667 | 10.86
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Planning
TSPi Weekly Status Report - Form WEEK
Name | Gabriel Castillo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 26.5667
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned | Percentage
Team Member Weekly Data |  |  | Planned | Actual | Value | Value | Completed
Planning Manager |  |  | 15 | 26.5667 | 15 | 5 | 1
Development Manager
Team Leader
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 26.5667 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 5.3333 | 1 | 1 | 1
Requerimientos T1 |  |  | 1 | 6.7 | 1 | 1 | 1
Diseño T1 |  |  | 1.2 | 3.4167 | 1.2 | 1 | 1
Documentacion T1 |  |  | 0.6 | 6.0333 | 0.6 | 1 | 1
Code T1 |  |  | 7.66 | 3.55 | 7.66 | 1 | 1
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 1.5333 | 0.8 | 1 | 1
Totals |  |  | 13.46 | 26.5667 | 12.26
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Development
TSPi Weekly Status Report - Form WEEK
Name | Javier Virviescas | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 23.1667
Project hours this cycle to date |  |  | 15 | 23.1667
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 23.1667 | 15 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 23.1667 | 15
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 3.3333 | 1 | 1 | 1
Requerimientos T1 |  |  | 1 | 0 | 0 | 1 | 0
Diseño T1 |  |  | 1.2 | 4.3333 | 1.2 | 1 | 1
Documentacion T1 |  |  | 0.6 | 1 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 9.3333 | 7.66 | 1 | 1
Test T1 |  |  | 1.2 | 1.5 | 1.2 | 1 | 1
PostMortem T1 |  |  | 0.8 | 3.6667 | 0.8 | 1 | 1
Totals |  |  | 13.46 | 23.1667 | 11.86
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items